## Sheet1
Nokia Scrum Assessment
| As an agile citizen, I can assess a team’s behavior and compare it to current Scrum best practices, so I can consider changes that might increase productivity. |  | Spreadsheet provided by Westerly Consulting, LLC. |  | Each person on the team should answer one column in the "person" area below. Place a 1 in each row (in your column) where you feel you do what the item defines.
Company Name
| Team Name |  | Test | Score
| Type name here |  | Assessment 1: Iteration | 0
|  |  | Assessment 2: In-Sprint Testing | 0
| Scrum Inc. created this assessment and has the copyright. |  | Assessment 3: Sprint Stories | 0
|  |  | Assessment 4: Product Owner | 0
| Instructions |  | Assessment 5: Product Backlog | 0
● | Each person on a team should have a piece of paper |  | Assessment 6: Estimation | 0
● | There are 10 assessments |  | Assessment 7: Sprint Burndown | 0
● | Each assessment has a score from 0 to 10 |  | Assessment 8: Retrospection | 0
● | In each assessment, sum the “Acceptance Tests” scores that pass. |  | Assessment 9: ScrumMaster | 0
● | Total score will range from 0 to 100 |  | Assessment 10: Team | 0
● | Average the scores for team members to get the team score |  | Team Score | 0%
Assessment 1: Iteration
As a team, before we commit to a Sprint, we know its duration, so we deliver better rhythmic, synchronized value.
| Acceptance Tests (pick one): |  | Entry |  | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | Person 9 | Person 10 | Person 11 | Person 12
● | Variable, 4 < duration ≤ 6 weeks | 2 | 0%
● | Variable, duration ≤ 4 weeks | 4 | 0%
● | Constant for last 3 iterations, duration = 1 month | 5 | 0%
● | Constant for last 3 iterations, duration = 4 weeks | 6 | 0%
● | Constant for last 3 iterations, duration = 3 weeks | 8 | 0%
● | Constant for last 3 iterations, duration ≤ 2 weeks | 10 | 0%
| Sub-total |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assessment 2: In-Sprint Testing
As a team, we take joint responsibility for all testing, so our Sprint product has sufficient quality to be immediately deployable.
| Acceptance Tests (sum): |  | Entry |  | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | Person 9 | Person 10 | Person 11 | Person 12
● | Team creates some unit tests in-sprint | 1 | 0%
● | Team creates unit tests for each story in-sprint | 1 | 0%
● | Team tests each story prior to Sprint Review | 2 | 0%
● | Team tests each story immediately after coding | 2 | 0%
● | Team automates feature tests for each new story | 2 | 0%
● | Build system packages, deploys to stage or live, and runs all automated feature tests at least every 24 hours | 2 | 0%
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assessment 3: Sprint Stories
As a team, we commit to work only when backlog items conform to a Definition of Ready, so we generate business value fast.
| Acceptance Tests (sum): |  | Entry |  | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | Person 9 | Person 10 | Person 11 | Person 12
● | Sprint requirements are documented | 1 | 0%
● | Requirements are independent, well-prioritized stories | 1 | 0%
● | Stories start with this: “As a <stakeholder>, I can <do something>, so <business gains value>” | 2 | 0%
● | Stories have externally verifiable acceptance tests | 2 | 0%
● | Team has a written, enforced Story Definition of Ready | 2 | 0%
● | Team has a written, enforced Story Definition of Done | 2 | 0%
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assessment 4: Product Owner
As a team, a single Product Owner helps the team understand and prioritize value, so we generate profits long-term.
| Acceptance Tests (sum): |  | Entry |  | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | Person 9 | Person 10 | Person 11 | Person 12
● | A single external person (PO) prioritizes work | 2 | 0%
● | PO interrupts team work only during Scrum meetings | 2 | 0%
● | PO attends all Planning, Grooming, Review and most Standups | 2 | 0%
● | PO creates a product backlog, with stories estimated by the team before Sprint Planning | 1 | 0%
● | PO maintains a velocity-aware release roadmap | 1 | 0%
● | PO motivates team to reduce technical debt | 2 | 0%
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assessment 5: Product Backlog
As a team, we have a value-ranked backlog, so we can focus on work that will generate the most business value for the least effort.
| Acceptance Tests (sum): |  | Entry |  | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | Person 9 | Person 10 | Person 11 | Person 12
● | Team serves multiple prioritized Product Backlogs | 1 | 0%
● | Team serves a single prioritized Product Backlog | 2 | 0%
● | PO regularly discusses release burndown with team, and adjusts backlog priorities based on historic velocity | 1 | 0%
● | Stories more than 3 months out trend larger in effort | 1 | 0%
● | Team can explain the ROI of each story | 1 | 0%
● | PO assesses value (NPV, buy-a-feature) to rank stories | 2 | 0%
● | PO prioritizes cheap prototypes to test value early | 2 | 0%
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assessment 6: Estimation
As a team, our estimates are largely free of statistical bias, so stakeholders can rely on release forecasts and make more money.
| Acceptance Tests (sum): |  | Entry |  | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | Person 9 | Person 10 | Person 11 | Person 12
● | Team agrees to estimates before committing | 1 | 0%
● | PO, SM and non-developers do not supply estimates | 1 | 0%
● | Team carefully avoids anchor bias before estimation | 1 | 0%
● | Representatives or actual team creates poker estimates | 1 | 0%
● | Actual team creates poker estimates | 2 | 0%
● | Teams use reference stories to make estimates | 2 | 0%
● | Actual velocity is < +/-20% of estimated velocity | 2 | 0%
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assessment 7: Sprint Burndown
As a team, we know our progress toward completion of backlog items, so members can help with high-priority work-in-progress.
| Acceptance Tests (sum): |  | Entry |  | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | Person 9 | Person 10 | Person 11 | Person 12
● | Burndown exists, team knows where it is | 1 | 0%
● | Team reviews, adjusts tasks and burndown daily | 1 | 0%
● | Tasks have hour or point estimates estimates (or team makes tasks about the same size) | 2 | 0%
● | Tasks burn down only after whole task is done | 2 | 0%
● | Stories burn down (no tasking) after whole story is done | 2 | 0%
● | All team members know team’s historic Velocity | 1 | 0%
● | Team commits to sprint backlog at or below Velocity | 1 | 0%
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assessment 8: Retrospection
As a team, we review our processes, so we can sustainably improve productivity.
| Acceptance Tests (sum): |  | Entry |  | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | Person 9 | Person 10 | Person 11 | Person 12
● | Team conducts retrospectives at least every 2 months | 2 | 0%
● | Team conducts retrospectives after each Sprint | 2 | 0%
● | Team limits retrospective participation to team and SM. Team optionally invites PO and others or un-invites SM | 2 | 0%
● | Team uses sticky-notes/other tools to ensure all members participate and tracks follow-up | 2 | 0%
● | Team puts top process improvement in the backlog for next sprint with acceptance tests | 2 | 0%
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assessment 9: ScrumMaster
As a team, the ScrumMaster competently enforces process, removes impediments, and provides transparency, so we can focus well.
| Acceptance Tests (sum): |  | Entry |  | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | Person 9 | Person 10 | Person 11 | Person 12
● | SM understands Scrum and agile concepts deeply | 2 | 0%
● | SM performs no tasks in the Sprint | 1 | 0%
● | SM enforces rules established by the team | 1 | 0%
● | SM sees impediments early, and handles for the team | 2 | 0%
● | SM maintains and uses a prioritized impediments list | 1 | 0%
● | SM makes team’s progress transparent to outsiders | 2 | 0%
● | SM communicates well with team, other teams, managers, stakeholders and PO | 1 | 0%
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Assessment 10: Team
As a team, we work together effectively to releasing our software, so we can get software to users earlier and adapt rapidly.
| Acceptance Tests (sum): |  | Entry |  | Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | Person 9 | Person 10 | Person 11 | Person 12
● | 3 ≤ team size without counting SM or PO ≤ 7 | 2 | 0%
● | Team members volunteer (are not assigned) to tasks | 2 | 0%
● | At least 2 members can independently finish each task | 2 | 0%
● | Team collectively commits to Sprint goal and backlog | 1 | 0%
● | Team collectively fights impediments in-sprint | 1 | 0%
● | Team reduces technical debt every sprint | 2 | 0%
|  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0