## Sheet1
Nokia Scrum Assessment
|  | As an agile citizen, I can assess a team’s behavior and compare it to current Scrum best practices, so I can consider changes that might increase productivity. | Spreadsheet provided by Westerly Consulting, LLC.
Company Name
Type name here
|  | Team Name | Test | Score
|  | Type name here | Assessment 1: Iteration | 0
|  |  | Assessment 2: In-Sprint Testing | 0
|  | Scrum Inc. created this assessment and has the copyright. | Assessment 3: Sprint Stories | 0
|  |  | Assessment 4: Product Owner | 0
|  | Instructions | Assessment 5: Product Backlog | 0
| ● | Each person on a team should have a piece of paper | Assessment 6: Estimation | 0
| ● | There are 10 assessments | Assessment 7: Sprint Burndown | 0
| ● | Each assessment has a score from 0 to 10 | Assessment 8: Retrospection | 0
| ● | In each assessment, sum the “Acceptance Tests” scores that pass. | Assessment 9: ScrumMaster | 0
| ● | Total score will range from 0 to 100 | Assessment 10: Team | 0
| ● | Average the scores for team members to get the team score | Team Score | 0%
Assessment 1: Iteration
As a team, before we commit to a Sprint, we know its duration, so we deliver better rhythmic, synchronized value.
|  | Acceptance Tests (pick one): | Entry
| ● | Variable, 4 < duration ≤ 6 weeks: 2
| ● | Variable, duration ≤ 4 weeks: 4
| ● | Constant for last 3 iterations, duration = 1 month: 5
| ● | Constant for last 3 iterations, duration = 4 weeks: 6
| ● | Constant for last 3 iterations, duration = 3 weeks: 8
| ● | Constant for last 3 iterations, duration ≤ 2 weeks: 10
|  | Sub-total | 0
Assessment 2: In-Sprint Testing
As a team, we take joint responsibility for all testing, so our Sprint product has sufficient quality to be immediately deployable.
|  | Acceptance Tests (sum): | Entry
| ● | Team creates some unit tests in-sprint: 1
| ● | Team creates unit tests for each story in-sprint: 1
| ● | Team tests each story prior to Sprint Review: 2
| ● | Team tests each story immediately after coding: 2
| ● | Team automates feature tests for each new story: 2
| ● | Build system packages, deploys to stage or live, and runs all automated feature tests at least every 24 hours: 2
0
Assessment 3: Sprint Stories
As a team, we commit to work only when backlog items conform to a Definition of Ready, so we generate business value fast.
|  | Acceptance Tests (sum): | Entry
| ● | Sprint requirements are documented: 1
| ● | Requirements are independent, well-prioritized stories: 1
| ● | Stories start with this: “As a <stakeholder>, I can <do something>, so <business gains value>”: 2
| ● | Stories have externally verifiable acceptance tests: 2
| ● | Team has a written, enforced Story Definition of Ready: 2
| ● | Team has a written, enforced Story Definition of Done: 2
0
Assessment 4: Product Owner
As a team, a single Product Owner helps the team understand and prioritize value, so we generate profits long-term.
|  | Acceptance Tests (sum): | Entry
| ● | A single external person (PO) prioritizes work: 2
| ● | PO interrupts team work only during Scrum meetings: 2
| ● | PO attends all Planning, Grooming, Review and most Standups: 2
| ● | PO creates a product backlog, with stories estimated by the team before Sprint Planning: 1
| ● | PO maintains a velocity-aware release roadmap: 1
| ● | PO motivates team to reduce technical debt: 2
0
Assessment 5: Product Backlog
As a team, we have a value-ranked backlog, so we can focus on work that will generate the most business value for the least effort.
|  | Acceptance Tests (sum): | Entry
| ● | Team serves multiple prioritized Product Backlogs: 1
| ● | Team serves a single prioritized Product Backlog: 2
| ● | PO regularly discusses release burndown with team, and adjusts backlog priorities based on historic velocity: 1
| ● | Stories more than 3 months out trend larger in effort: 1
| ● | Team can explain the ROI of each story: 1
| ● | PO assesses value (NPV, buy-a-feature) to rank stories: 2
| ● | PO prioritizes cheap prototypes to test value early: 2
0
Assessment 6: Estimation
As a team, our estimates are largely free of statistical bias, so stakeholders can rely on release forecasts and make more money.
|  | Acceptance Tests (sum): | Entry
| ● | Team agrees to estimates before committing: 1
| ● | PO, SM and non-developers do not supply estimates: 1
| ● | Team carefully avoids anchor bias before estimation: 1
| ● | Representatives or actual team creates poker estimates: 1
| ● | Actual team creates poker estimates: 2
| ● | Teams use reference stories to make estimates: 2
| ● | Actual velocity is < +/-20% of estimated velocity: 2
0
Assessment 7: Sprint Burndown
As a team, we know our progress toward completion of backlog items, so members can help with high-priority work-in-progress.
|  | Acceptance Tests (sum): | Entry
| ● | Burndown exists, team knows where it is: 1
| ● | Team reviews, adjusts tasks and burndown daily: 1
| ● | Tasks have hour or point estimates estimates (or team makes tasks about the same size): 2
| ● | Tasks burn down only after whole task is done: 2
| ● | Stories burn down (no tasking) after whole story is done: 2
| ● | All team members know team’s historic Velocity: 1
| ● | Team commits to sprint backlog at or below Velocity:1
0
Assessment 8: Retrospection
As a team, we review our processes, so we can sustainably improve productivity.
|  | Acceptance Tests (sum): | Entry
| ● | Team conducts retrospectives at least every 2 months: 2
| ● | Team conducts retrospectives after each Sprint: 2
| ● | Team limits retrospective participation to team and SM. Team optionally invites PO and others or un-invites SM: 2
| ● | Team uses sticky-notes/other tools to ensure all members participate and tracks follow-up: 2
| ● | Team puts top process improvement in the backlog for next sprint with acceptance tests: 2
0
Assessment 9: ScrumMaster
As a team, the ScrumMaster competently enforces process, removes impediments, and provides transparency, so we can focus well.
|  | Acceptance Tests (sum): | Entry
| ● | SM understands Scrum and agile concepts deeply: 2
| ● | SM performs no tasks in the Sprint: 1
| ● | SM enforces rules established by the team: 1
| ● | SM sees impediments early, and handles for the team: 2
| ● | SM maintains and uses a prioritized impediments list: 1
| ● | SM makes team’s progress transparent to outsiders: 2
| ● | SM communicates well with team, other teams, managers, stakeholders and PO: 1
0
Assessment 10: Team
As a team, we work together effectively to releasing our software, so we can get software to users earlier and adapt rapidly.
|  | Acceptance Tests (sum): | Entry
| ● | 3 ≤ team size without counting SM or PO ≤ 7: 2
| ● | Team members volunteer (are not assigned) to tasks: 2
| ● | At least 2 members can independently finish each task: 2
| ● | Team collectively commits to Sprint goal and backlog: 1
| ● | Team collectively fights impediments in-sprint: 1
| ● | Team reduces technical debt every sprint: 2
0